Project Plan

Company 10

Martin Ruzicka

Version 0.5

# Status

|  |  |  |
| --- | --- | --- |
| Reviewed | Martin Ruzicka, Hans Sanell, Jonas Mattsson, Henrik Nilsson, Vamsi Seshabhattaru | 2010-02-03 |
| Approved | Sebastian Rehnby (PM) | 2010-02-05 |

# Project identity

Company 10, 2010

Chalmers University of Technology, MPSEN

|  |  |  |  |
| --- | --- | --- | --- |
| **Name** | **Responsibility** | **Phone** | **E-mail** |
| Martin Ruzicka | Software Architect | 070 219 20 81 | [ruzicka@student.chalmers.se](mailto:ruzicka@student.chalmers.se) |
| Jonas Mattsson | Database Designer | 070 58 18 095 | [emattsso@student.chalmers.se](mailto:emattsso@student.chalmers.se) |
| Hans Sanell | Software Architect | 073 53 55 210 | [hansn@student.chalmers.se](mailto:hansn@student.chalmers.se) |
| Sebastian Rehnby | Project Manager | 0735 080 850 |  |
| Vamsi Seshabhattaru | Quality Manager | 0739 190 703 | [vamsi@student.chalmers.se](mailto:vamsi@student.chalmers.se) |
| Henrik Schulze Nilsson | Graphical Designer | 0733 643 501 | [henrnil@student.chalmers.se](mailto:henrnil@student.chalmers.se) |

[suit-group-10@googlegroups.com](mailto:suit-group-10@googlegroups.com)

**Client:** Central Operative & Independent Retailers Acquirer, 9 Downing St, Westminster, London SW1A, UK

**Client Contact:** Peter Arch, +44 333 757589, [peter.arch@coira.com](mailto:peter.arch@coira.com)

**Supervisor:** Per Zaring

# Content

1. Client 5

2. Overall project description 5

2.1. Purpose 6

2.2. Deliverables 6

2.3. Demarcations 6

3. Phases 6

3.1. Pre-project activities with time budget 6

3.2. Project activities with time budget 6

3.3. Post-project activities with time budget 7

4. Organization plan 7

4.1. Organization per phase 7

4.2. Work breakdown structure and responsibility areas 8

5. Document plan 8

6. Development approach 9

7. Plan for training and competence development 9

7.1. Internal training 10

7.2. Client training 10

8. Report routines 10

9. Meeting routines 10

10. Resource allocation plan 10

10.1. People 10

10.2. Equipment 10

10.3. Facilities 10

10.4. Finance 11

11. Milestones and decision gates 11

11.1. Milestones 11

11.2. Decision gates 11

12. Estimations/activity 12

13. Time plan 13

14. Test plan 13

15. Risk analysis 13

15.1. Risks 13

15.2. Issues 14

# Document History

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Version** | **Date** | **Changes** | **Responsible** | **Approved** |
| 0.5 | 2010-02-05 | Final overlook | MR | SR |
| 0.4 | 2010-02-03 | Updated from review | MR | SR |
| 0.3 | 2010-02-03 | Change in template | MR | SR |
| 0.2 | 2010-02-02 | Merged to Word-template | MR | SR |
| 0.1 | 2010-02-01 | First version | SR, VS | SR |

Client

Central Operative & Independent Retailers Acquirer (Coira).

Overall project description

Coira wants a web-based portal where customers from all corners of the world can purchase products. This portal should consist of three parts. The portal itself, called MUW (Mall Unlimited Well), that contains the interface towards the customer and the database of available products. A system for handling the suppliers and the purchases, called PUW (Purchase Unlimited Well), that contains the list of approved suppliers and their products. Also, a system for transporters and logistics is needed, called LUW (Logistics Unlimited Well), that contains all approved transporters and there routes. These systems cooperate so that when a customer orders something through MUW, a request is sent to PUW to order the goods from the supplier and a separate request is sent to LUW to book a transport for the purchased goods from the supplier to the customer. All systems should be fault tolerant and provide high availability. All systems must be secure and the integrity of customers, suppliers and transporters must have the highest priority.

MUW handles all interaction with the customer. MUW displays all available products; there details, their price and how long it will take to deliver. MUW also handles the customers orders, displays information and options about orders, such as where they are and if there is any problems, and notifies the customer if there is any hiccups along the way. MUW's graphical interface will provide context-sensitive help at all levels of the interface. At purchase, MUW should find an optimal combination of supplier and transporter. MUW contains the database of available products, their status and suppliers, as well as the customer register. MUW must support several languages and it must be easy to extend the number of languages supported. MUW will also collect statistics about purchases and use these to make predictions about demands and ask PUW to make sure that there is enough supply to satisfy the demand.

PUW is, upon purchase, to contact the chosen supplier and book the products specified. PUW will also keep track of suppliers and update there status in MUW's database. PUW will select suppliers that should undergo a quality review given certain conditions. PUW also has to notify Coira employees if there is not enough suppliers in the system to meet the demand as predicted by MUW, so that new suppliers may be acquired. PUW will also handle delivery notes and send all required data to Coiras financial system.

LUW will be responsible for handling logistics and transportation and keeps track of transporters and their routes. Upon purchase, LUW will book suitable transportation and produce all the needed papers, such as bills of lading and import licenses. LUW is responsible for updating the status of orders and where a particular order is physically. To be able to do this, LUW must accept input from a number of different sources so that the companies that handle the actual transport can update regardless of internal system used. LUW shall utilize a GIS company to compute distances and time consumption. LUW must also make sure that each transport is as profitable as possible with very few, but existing, exceptions. LUW must also allow independent transporters to use the system to plan transports and routes. This includes transports that have nothing to do with Coira. In this case the system is called "Logistics at Transporters" (LaT). In case the system is used this way, the content in the transporters area must be exclusive to that transporter. LUW should notify MUW and Coira personnel in case any hiccups occur.

* 1. Purpose

For Coira to be able to reach and service worldwide customers and to streamline and enhance the process from placed order to delivery, in a way that is as cost efficient and fast as possible.

* 1. Deliverables
* Project Directives
* Project Plan
* Development plan
* Software Requirements
* Test Plan
* Test Report
* Project Report
* Final software system
* System documentation

This system will be delivered to Coira and Company 10 will assist in the final deployment and integration of the system with Coira's existing infrastructure.

* 1. Demarcations

The project is to be executed with limited resources including human resources and development time. The main concentration area of our company given the limited scope is to focus on the basic but the most relevant and the core functionality of the project including the three main concepts of the systems i.e. MUW, LUW and PUW.

Phases

The project has been divided into various phases and the team members given individual tasks during the various phases of the project

* 1. Pre-project activities with time budget

The pre-project activities include formal team meeting of the team members and discussing the project related issues such as the roles of each team member.

* 1. Project activities with time budget

After the completion of the pre-project activities, the project activities will be started including the project planning, development planning, software requirement specifications, requirement analysis, design and development of project, validation, verification and testing and documentation of the project.

* 1. Post-project activities with time budget

After the project activities have been completed, the post project activities which include reporting the updates of the project and the demonstration of the final product to the client/acquirer and incorporation of minor modifications or alterations suggested by the client wherever feasible.

Organization plan

The organization of the team will be consistent throughout the project. Depending on workload and phase, team members should offer assistance to the person responsible for the highest prioritized task/deliverable. In nothing else is specified, the responsibility for each activity should be determined by the roles specification.

* 1. Organization per phase

The different phases will not change the responsibilities for a given task, but assistance should be offered to the member responsible based on the nature of the tasks in each phase. A visualization of the organizational structure is shown in Figure 1.




Figure - Organizational structure.

* 1. Work breakdown structure and responsibility areas

The project has been divided into various key role areas and the tasks have been allocated to the team members accordingly. Each team member has been given a primary role and a back up or a secondary role as a risk mitigation step.

The main key roles and the team members for each of the phases has been distributed as follows:

|  |  |  |
| --- | --- | --- |
| **Role** | **Lead** | **Second** |
| Project Manager | Sebastian Rehnby | Martin Ruzicka |
| Software Architecture | Hans Sanell | Martin Ruzicka |
| Database Designer | Jonas Mattsson | Henrik Schulze Nilsson |
| Test/Quality Manager | Vamsi Seshabhattaru | Hans Sanell |
| Graphical Designer: | Henrik Schulze Nilsson | Jonas Mattsson |
| Clerical Role | The clerical role is to be distributed to all the team members on a rotational time bound schedule. | |

Document plan

The following table describes the document deliverables and their deadlines.

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Document** | **Approved by** | **Purpose** | **Distributed to** | **Deadline** |
| Project Directives | PM/Team | Define the project background and goals | Team | 2010-01-28 |
| Project Plan | PM | Outline execution of project and estimate resources | Team | 2010-02-05 |
| Development Plan | PM | Define and estimate tasks related to developing the proposed system | Team | 2010-02-10 |
| Software Requirements | PM/Client | Gather system requirements from the project description and prioritize them | Client/Team | 2010-02-05 |
| Test Plan | TM | Define the level of testing and test cases for the system | Team | 2010-02-17 |
| Test Report | TM | Analyzing test results and feedback to developers, and also to prove the quality of the system to client | Client/Team | 2010-02-24 |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project Report | PM | Summarize the project and evaluate the final result | Client/Team | 2010-03-03 |
| System Documentation | PM/Client | A manual for the system user | Client | 2010-03-03 |

Development approach

The project will be developed using an incremental development approach, where each iteration is a variation of the V-model development process. This means that each iteration will itself contain activities such as designing, implementation and testing. The big difference from the complete V-model process in each iteration is that the requirements analysis will be completed before the first iteration of the development cycle. Figure 2 shows the graphical visualization of the development process.




Figure - The development process.

Plan for training and competence development

The group roles distribution is based on each of the members’ previous experiences and areas of expertise.

* 1. Internal training

The team members will be allowed to take part in any task or activity that they feel they can benefit from in order to increase their level of competence in a certain technological area.

* 1. Client training

It will be possible for the client to establish a post-delivery support agreement, to provide the client with support after the integration and initial stages of deployment. Company 10 will not provide any training besides the user documentation.

Report routines

Every Monday morning at 8.00AM at the latest, each team member will submit a weekly status report to the PM. The report should include a time sheet for the previous week for hours spent on the project, as well as a description of the project progress and issues.

Meeting routines

The time for each meeting will be decided beforehand on the preceding meeting, and added to the official project calendar. A group room should be reserved beforehand and the reservation should be communicated to the group.

The clerical function for the meetings will be rotated week wise. The person responsible will take notes and upload the protocol to the common Subversion repository in the folder 'protocols'. Any questions regarding the content of the protocols should be communicated to the Project Manager, and the protocol should be revised accordingly.

Resource allocation plan

Resources needed for the execution of the project will be provided by Company 10 and Chalmers University of Technology.

* 1. People

The entire work force at Company 10 will be committed to this project, focusing on their respective area of responsibility.

* 1. Equipment

Company 10 will use its own resources in terms of equipment for the execution of this project. Tools and equipment required will include desktop computers and development servers.

* 1. Facilities

Facilities required for meetings and collaborative development sessions will be provided by Chalmers University of Technology.

* 1. Finance

No financing is required for this project. Any unexpected costs will be covered by the client.

Milestones and decision gates

The project defines a set of milestones and decision gates to keep the project on track. The following sections describes these.

* 1. Milestones

A number of milestones have been defined to be able to measure project progress. In most cases, milestones are related to the completion of various deliverables.

|  |  |  |
| --- | --- | --- |
|  | **Description** | **Date** |
| M1 | Project organization defined and approved | 2010-01-20 |
| M2 | Project Directives verified and approved | 2010-01-25 |
| M3 | Project activities defined | 2010-01-28 |
| M4 | Project plan verified and approved | 2010-02-05 |
| M5 | Completed Software Requirements Specification | 2010-02-05 |
| M6 | Development process defined and approved | 2010-02-08 |
| M7 | Development Plan verified and approved | 2010-02-10 |
| M8 | Design specification completed and approved | 2010-02-15 |
| M9 | Implementation proposal completed | 2010-02-15 |
| M10 | Test plan completed and approved | 2010-02-17 |
| M11 | System implementation completed | 2010-03-02 |
| M12 | System testing and verification successfully completed | 2010-03-02 |
| M13 | System demonstration completed | 2010-03-03 |
| M14 | System documentation finalized and approved | 2010-03-03 |
| M15 | Project completed, entering maintenance mode | 2010-03-03 |

* 1. Decision gates

A continuous evaluation of the passing of milestones will be done by using a number of internal Decision Gates (DG). To be able the pass most DGs, some deliverables need to be completed beforehand. These deliverables are defined in the description column in the following table.

|  |  |  |
| --- | --- | --- |
| **#** | **Description** | **Date** |
| 0 | Approve Project Directives | 2010-01-25 |
| 1 | Approve Project Plan | 2010-02-01 |
| 2 | Approve Software Requirements Specification | 2010-02-05 |
| 3 | Approve Development Plan | 2010-02-10 |
| 4 | Approved Test Plan | 2010-02-17 |
| 5 | Review test execution results | 2010-02-24 |
| 6 | Review Project Report and Postmortem Analysis | 2010-03-02 |

Estimations/activity

The terminology used for this project is defined as follows. Higher order phases are referred to as activities. The work packages included in each activity are referred to as tasks. Each task includes a number of features (for development tasks) or deliverables (for management tasks).

An example would be the activity of "System design". In this case, a task would be to "Develop system diagrams (ERD, Class Diagrams)", and a development task would be "Develop ordering ERD-diagram" or "develop Class Diagram for MUW". The activities are described in the following table and a detailed time plan can be found in Appendix A.

|  |  |  |  |
| --- | --- | --- | --- |
| **#** | **Activity** | **Description** | **Estimated time (h)** |
| 1. | Organize project team | The initial process of defining the team organization and roles distribution | 28 |
| 2. | Analyze project background and goals | This activity is concerned with gathering information and getting familiar with the project specification and the purpose and goals of the project. | 48 |
| 3. | Project Planning | This activity of dealing with the outlay of the project with estimations related to resources required, and the overall plan of the project and also the timing issues and the various deadlines to be decided. | 60 |
| 4. | Development Planning | This activity is concerned with defining the features of each tasks, and producing a development timeline. | 64 |
| 5. | Analyze system requirements | This phase of project would be to look into the specific requirements of the project and analysis of the same. This phase is one of the most crucial and important phases of the whole project as it deals with understanding and analysis of the project requirements. | 178 |
| 6. | System design | This activity deals with defining the software architecture and test plan of the system to be implemented. | 82 |
| 7. | System implementation & testing | This phase of the project deals with the implementation of the software design, and also the process of testing the implemented system. | 202 |
| 8. | System demonstration | Demonstrating the final system to the client and other stakeholders. | 52 |
| 9. | Documentation | This phase of the project deals with the documentation of the system and producing a final project report. | 46 |

Time plan

See Appendix A.

Test plan

Testing is an important part of any project and it is the same for our product as well. But due to the limited resources and time available, the testing phase would mainly be concerned with the basic functional requirements and design requirements as defined in the Software Requirements Document of this project. The main focus would be to individually test the three different components of the project, the accessibility of the web portal on various operating systems and the availability of the web-based system. Also the security of the system will be tested to check that the system information is secure and make sure it provides a secure pathway for the customers/users to make financial transactions and the availability of complete product information to the customers. These are some of the areas in which we plan to test extensively but given the time limitations we will only test the high-prioritized requirements.

The project plan defines an iterative development approach and testing should be carried out in each iteration. One of the main concerns is the limited time frame available and hence testing the product and its component in each iteration will help in developing a better product and a thoroughly tested and a reliable system. Company 10 will also test the final integrated model at the end of the final iteration.

Risk analysis

* 1. Risks

Given the limited timeframe of this project, the by far greatest risk is the one of not having the time to fully implement the complete system by the delivery date. This is a risk that both Company 10 and the client is fully aware of, and several meetings and discussions have been held in order to find a solution an minimize the probability and impact of this scenario.

The client and Company 10 have agreed, based on the incremental development process chosen, that the client will be taking an active role in the prioritizing of system requirements. Through this process, the client will identify the key requirements most important to the client. Company 10 will aim to deliver a system meeting the highest priority requirements by the delivery date.

Also, the risk of not passing a decision gate (DG) at the targeted deadline date is very probable. The proposed solution for this is to not consider these deadlines as written in stone, but to give an estimate of when during the project timeline a DG should be passed. If two DG:s are closely coupled or dependent, it might make more sense to push the date on one of them in order to complete the work needed for both. Then both of them can be passed rather quickly.

* 1. Issues

No obvious issues can be foreseen.

# References

[1] Unlimited Well, Project Specification, 2010

[2] Internal Requirements Specification draft, 2010

[3] SWEBOK, 2004

[4] Project Directives, 2010